## projects
id | title | type | pillar | acct_code | owner | sponsored | sponsorship_type | sponsorship_other | status | format | content_generator | committee_name | funding_source | program_partner_name | budget | est_hours | draft_delivered | draft_commented | draft_completed | layout1_delivered | layout1_commented | layout2_delivered | layout2_approved | print_date | go_live_date | notes | pct_override | confirmed_pending
4 | ConstructSteel White Paper | White paper | Program Partnership | 905a | DS | Yes | Program Partnership | nan | Obligatory sponsor deliverable | Digital | Client + RTL | nan | Program Partner | constructsteel | 62500 | 0 | 2026-04-07 | 2026-04-17 | 2026-05-01 | 2026-05-15 | 2026-05-29 | 2026-06-12 | 2026-06-26 | nan | 2026-07-07 | nan | 0 | Confirmed
2 | 2026 Americas Conference Proceedings | White paper | Conference Sponsorship | 703 | DS | Yes | Other | Conference Sponsor | Internal commitment | Digital | RTL | nan | Program Partner | constructsteel | 62500 | 31 | 2026-03-31 | 2026-04-07 | 2026-04-14 | 2026-04-21 | 2026-04-28 | 2026-05-05 | 2026-05-12 | nan | 2026-06-01 | nan | 0 | Confirmed
6 | Sobha Executive Dialogue Series Written Summary | White paper | Program Partnership | 906a | DS | Yes | Program Partnership | nan | Obligatory sponsor deliverable | TBD | Client + RTL | nan | Program Partner | Sobha | 0 | 0 | 2026-05-15 | 2026-05-22 | 2026-06-05 | 2026-06-19 | 2026-06-26 | 2026-07-10 | 2026-07-17 | nan | 2026-09-01 | Sobha still TBD on participation due to war | 0 | Confirmed
3 | 2026 VU Summit Proceedings | Book | Committee-Driven | 703 | DS | Yes | Program Partnership | nan | Obligatory sponsor deliverable | TBD | Conference Speakers | nan | Program Partner | constructsteel | 62500 | 31 | 2026-05-14 | 2026-05-21 | 2026-06-04 | 2026-06-18 | 2026-06-25 | 2026-07-09 | 2026-07-17 | nan | 2026-09-21 | Not confirmed | 0 | Pending
1 | 2025 Asia Conference Proceedings | Book | Conference Sponsorship | 703 | DS | Yes | Other | Conference Sponsor | Obligatory sponsor deliverable | TBD | Conference Speakers | nan | Program Partner | constructsteel | 10000 | 5 | 2026-02-23 | 2026-02-26 | 2026-03-09 | 2026-04-09 | 2026-04-16 | 2026-04-23 | 2026-04-30 | nan | 2026-05-04 | nan | 0 | Confirmed
5 | CPF/CW Carbon v Code Final Report | PDF report | Commissioned Research | 910 | DS | Yes | Commissioned Research | nan | Obligatory sponsor deliverable | Digital | RTL | nan | Commissioned Research | nan | 8135 | 0 | nan | nan | nan | nan | nan | nan | nan | nan | 2026-12-12 | nan | 0 | Confirmed
7 | Sobha White Paper: Innovation as the Outcome of Integration | White paper | Program Partnership | 906a | DS | Yes | Program Partnership | nan | Obligatory sponsor deliverable | Digital | Client + RTL | nan | Program Partner | Sobha | 20692 | 150 | 2026-05-15 | 2026-05-22 | 2026-06-05 | 2026-06-19 | 2026-06-26 | 2026-07-10 | 2026-07-17 | nan | 2026-09-01 | Sobha still TBD on participation due to war | 0 | Confirmed
8 | Talls Solutions White Paper - Brazil’s Vertical Urbanism | White paper | Program Partnership | 904a | DS | Yes | Program Partnership | nan | Obligatory sponsor deliverable | Digital | Client + RTL | nan | Program Partner | FG ¦ Talls | 26375 | 150 | 2026-05-15 | 2026-05-22 | 2026-06-05 | 2026-06-19 | 2026-06-26 | 2026-07-10 | 2026-07-17 | nan | 2026-09-01 | nan | 0 | Confirmed
10 | Global Activity Series: Americas (Q1) | Data study | Program Partnership | 906a | IW | Yes | Program Partnership | nan | Project completed | Digital | RTL | nan | Program Partner | Sobha | 11005 | 80 | 2026-02-16 | 2026-02-23 | 2026-02-27 | 2026-03-02 | 2026-03-09 | 2026-03-12 | 2026-03-19 | nan | 2026-04-08 | nan | 0 | Confirmed
11 | Vertical Urbanism Index Report | PDF report | Program Partnership | 904a | IW | Yes | Program Partnership | nan | Project completed | Digital | RTL | nan | Program Partner | FG ¦ Talls | 22875 | 0 | 2025-12-24 | 2026-01-08 | 2026-01-09 | 2026-01-09 | 2026-01-12 | 2026-01-14 | 2026-01-16 | nan | 2026-01-30 | nan | 0 | Confirmed
12 | Global Trends and Forecasts 2026 | Data study | Program Partnership | 906a | IW | Yes | Program Partnership | nan | Project completed | Digital | RTL | nan | Program Partner | Sobha | 14531.25 | 105 | 2026-01-05 | 2026-01-09 | 2026-01-12 | 2026-01-20 | 2026-01-22 | 2026-01-29 | 2026-01-30 | nan | 2026-02-06 | nan | 0 | Confirmed
13 | Vertical Urbanism 6: Q1 2026 | Magazine | Advertising and Sales-Driven | 701 | DS | Yes | VU Advert | nan | Project completed | Digital | External Contributors | nan | Conference Sponsor | nan | 0 | 95 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-30 | 2025-12-01 | 2025-12-08 | 2025-12-15 | nan | 2026-01-22 | nan | 0 | Confirmed
14 | RTL Capacities Brochure | PDF report | Commissioned Research | 916 | RD | No | nan | nan | Project completed | Digital | RTL | nan | Conference Sponsor | nan | 0 | 150 | 2026-02-13 | 2026-02-20 | 2026-02-25 | 2026-02-13 | 2026-02-18 | 2026-02-20 | 2026-02-25 | nan | 2026-02-27 | nan | 0 | Confirmed
15 | Global Activity Series: Europe (Q2) | Data study | Program Partnership | 906a | IW | Yes | Program Partnership | nan | Obligatory sponsor deliverable | Digital | RTL | nan | Program Partner | Sobha | 10385 | 75 | 2026-05-13 | 2026-05-20 | 2026-05-22 | 2026-06-01 | 2026-06-08 | 2026-06-13 | 2026-06-20 | nan | 2026-06-30 | nan | 0 | Confirmed
16 | Global Activity Series: Middle East (Q3) | Data study | Program Partnership | 906a | IW | Yes | Program Partnership | nan | Obligatory sponsor deliverable | Digital | RTL | nan | Program Partner | Sobha | 10385 | 75 | 2026-08-26 | 2026-09-02 | 2026-09-04 | 2026-09-14 | 2026-09-21 | 2026-09-25 | 2026-10-02 | nan | 2026-10-26 | nan | 0 | Confirmed
17 | Global Activity Series: Asia (Q4) | Data study | Program Partnership | 906a | IW | Yes | Program Partnership | nan | Obligatory sponsor deliverable | Digital | RTL | nan | Program Partner | Sobha | 10385 | 75 | 2026-10-14 | 2026-10-21 | 2026-10-23 | 2026-11-02 | 2026-11-09 | 2026-11-13 | 2026-11-20 | nan | 2026-12-07 | nan | 0 | Confirmed
18 | Sustainability Database and Dashboard | Data study | Program Partnership | 905a | WM | No | nan | nan | Internal commitment | Digital | Client + RTL | nan | Program Partner | MVRDV NEXT (in-kind) | 0 | 200 | 2026-03-31 | 2026-04-07 | 2026-04-14 | 2026-04-21 | 2026-04-28 | 2026-05-05 | 2026-05-12 | nan | 2026-09-01 | nan | 0 | Confirmed
19 | Tall + Urban v9 | Book | Advertising and Sales-Driven | 702 | SU | No | nan | nan | Internal commitment | Print | External Contributors | nan | Sales | nan | 0 | 307 | 2026-05-14 | 2026-05-21 | 2026-06-04 | 2026-06-18 | 2026-06-25 | 2026-07-09 | 2026-07-17 | 2026-08-01 | nan | nan | 0 | Confirmed
20 | Vertical Urbanism 7: Q2 2026 | Magazine | Advertising and Sales-Driven | 701 | DS | Yes | VU Advert | nan | Internal commitment | Digital | External Contributors | nan | Sales | nan | 0 | 95 | 2026-03-16 | 2026-03-23 | 2026-04-06 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | nan | 2026-06-01 | nan | 0 | Confirmed
21 | Vertical Urbanism 8: Q3 2026 | Magazine | Advertising and Sales-Driven | 701 | DS | Yes | VU Advert | nan | Internal commitment | Both | External Contributors | nan | Sales | nan | 0 | 95 | 2026-06-18 | 2026-06-25 | 2026-07-09 | 2026-07-23 | 2026-07-30 | 2026-08-06 | 2026-08-13 | 2026-08-20 | 2026-09-21 | nan | 0 | Confirmed
22 | Wind Engineering of High-Rise Buildings | Book | Committee-Driven | 916 | RD | Yes | Commissioned Research | nan | Internal idea | TBD | Committee | Wind Engineering Cmte | Commissioned Research | nan | 40000 | 0 | nan | nan | nan | nan | nan | nan | nan | nan | 2026-09-21 | nan | 0 | Confirmed
9 | White Paper MVRDV NEXT | White paper | Program Partnership | 905a | WM | Yes | Program Partnership | nan | Obligatory sponsor deliverable | TBD | Client + RTL | nan | Program Partner | MVRDV NEXT (in-kind) | 0 | 0 | 2026-05-15 | 2026-05-22 | 2026-06-05 | 2026-06-19 | 2026-06-26 | 2026-07-10 | 2026-07-17 | nan | 2026-09-01 | nan | 0 | Confirmed
23 | Outdoor Wind Comfort Regulation Guide | Book | Committee-Driven | 916 | RD | Yes | Commissioned Research | nan | Internal idea | TBD | Committee | Wind Engineering Cmte | Commissioned Research | nan | 0 | 0 | nan | nan | nan | nan | nan | nan | nan | nan | 2026-12-31 | nan | 0 | Confirmed
24 | Research Roadmap 2.0 | PDF report | Committee-Driven | 704 | DS | No | nan | nan | Internal idea | Both | External Contributors | nan | None | nan | 0 | 0 | 2026-05-15 | 2026-05-22 | 2026-06-05 | 2026-06-19 | 2026-06-26 | 2026-07-10 | 2026-07-17 | 2026-07-30 | 2026-09-21 | nan | 0 | Pending
25 | RFR China Façade Book | Book | Other Sponsorship | 705 | DS | Yes | Commissioned Research |  | Internal commitment | Print | Other CVU Team |  | Commissioned Research |  | 0 | 0 | 2026-05-14 | 2026-05-21 | 2026-06-04 | 2026-06-18 | 2026-06-25 | 2026-07-09 | 2026-07-17 | 2026-08-01 |  | Unlikely to happen | 0 | Pending

## settings
rtl_hourly_rate | 91.03